## Instructions
Instructions Planned M&R Budget Control Tool
1 | Introduction
Planned M&R is defined as dry dockings, (damage) repairs and modifications with a 'project approach'.
Planned M&R projects need to be planned well before the start of activities. This plan should contain scope, planning and budget of the project.
The planned M&R project plan should be prepared taking into consideration minimizing running M&R expenses during the period in between
two special surveys.
The general purpose of the planned M&R budget control tool is to give technical superintendents a tool to budget planned M&R projects before the
execution of the project, and to control costs during the execution of the project. It should give guidance to monitor expenses and commitments
thereto in comparison to the budget.
By continious tracing of commitments and forecasts superintendents should be able to have complete insight in the financial progress of the
planned M&R project. Any budget overruns can be anticipated at an early stage and corrective measures can be taken in time.
In a broader sence, the finalized planned M&R project plans (including evaluations on actuals vs budget) should give Smit Lamnalco a tool to
benchmark M&R projects in respect of costs and time.
The planned M&R budget control tool consists of 3 main parts:
1 | Planned M&R Project Plan
2 | Planned M&R Daily Report
3 | Planned M&R Project Plan - details per cost coding main group + damages & modifications
The project plan contains general information and summerized financial information about the planned M&R project. This page is used for budget approval
before the execution of the project. This page is also used to evaluate the project final results in comparison to the budget at the end of the planned M&R project.
The daily report contains progress information and summerized financial information at a certain moment/period during the planned M&R project execution.
The page is used to monitor the financial status and the progress of the project. Items which have financial impact or influence the progress of the project are reported on this page.
The project plan details contains the corresponding details of each expense category. These pages gives the superintendent the possibility to budget and monitor expenses
in detail. There are 'detail'-worksheets for all expense categories, which are further explained below:
1 | Flag state-, class- and management, consumables, transportation
2 | Ship’s hull, conservation.
3 | Equipment and systems for crew and passengers.
4 | Diesel engines, flexible couplings for DE’s, generators.
5 | Ship propulsion and steering equipment.
6 | Ship specific equipment.
7 | Ship common systems deck department.
8 | Ship common systems engine department.
9 | Alongside repair and dry docking
10 | Damages
11 | Modifications
Each expense category can be budgeted on the separate -worksheets. The 'detail'-worksheet per expense category should be filled
with all individual work specifications (W.S.) budgeted. After budget approval, for each work specification the corresponding purchase order (at moment of issuing) and
purchase invoice (at moment of receipt) can be reported. The technical superintendent can monitor the costs compared to the
project budget and has an overview of the financial status of the project at any time.
Work Variation Forms (WVF) are used to monitor additional and less work including the financial consequenses and influence on the work planning, if any.
Repair of damages and modifications shall be budgeted and monitored separately from the planned M&R. Therefore separate
detail'-worksheets are in place for these categories (damages and modifications).
In general the following rules are used for input:
Cells for input
Fixed value input |  | 0000
Estimated value input |  | 0000
Note: Start with entering the project specific details, such as vessel name, dates, etc. in the yellow marked fields on the Planned M&R Project Plan page.
2 | Planned M&R - Project Plan page
Contact the financial department to obtain a Project no. This project number is used to allocate the actual project expenses in the accounting system.
Based on a combination of Project no., Vessel ID, month and year of demobilisation each planned M&R project has an assigned reference ID.
The planned M&R project ID reference in combination with the number of the sub category (1 to 11, see above) must be used by suppliers, and shall be included in the invoices.
Explanatory notes in reference to the planned M&R project plan can be made in the remark field on line level.
Amounts will be filled in the 'detail'-worksheets of the planned M&R budget control tool. Reference is made to item 3 below, M&R project plan - details.
Applicant- , consent- and approval level will be adjusted, based on total amount of the project plan.
This M&R project plan page is also to be used for additional authorization, required in case of an budget overrun of > 5%.
3 | Details'-worksheets: Planned M&R Group 1 - 9, Group 10 Damages and Group 11 Modifications
For the detailed planning and for cost control, the M&R project plan - 'detail'-worksheet (per Expense Category) is used.
The totals per project plan expense category are linked to the corresponding totals in the M&R project plan page and Planned M&R Daily Report page.
The M&R project plan should be filled out in USD. For the purchases in other currencies corresponding conversion rates can be filled in.
After final approval of the budget, cost control is monitored by using the commitment, forecast and actual columns.
Total commited: answers the question "when the project is stopped today what is the amount of money spent."
Total forecast: answers the question "what is the total amount of money what we expect to spent by the end of the M&R project."
Total actual: is the total amount booked in the ERP system.
The final evaluation of actuals vs budget/forecast shall be made when all the work is completed.
Consent/approval of the evaluation is in line with the authorization levels for the planned M&R project plan budget.
The financial deptartment will accrue in the financial books the estimated actual costs still to be expected. This is determined from the difference
between forecast/commitments and actual received and approved (= booked) purchase invoices.
The finance dept will monitor actual purchase invoices in comparison to the accrual.
When needed each consent level can add some comments to the final evaluation.
In case of a damage to be claimed from insurers please contact the group insurance manager for insurance claim ID no. and insurance deductible amount.
This deductable amount will be for account of SL.
The explantory notes can be used to further explain the background and nature of the damage and the corresponding repair.

## Planned M&R Project Plan
FRM-OFF-04-Site Specific Novo-002
|  | BUDGET CONTROL TOOLS |  |  |  | File 04 / Папка 04
Retention 3 Year / Срок хранения 3 года
Planned M&R Project Plan
Name TSI-P : |  |  |  | Project Plan Currency: | USD
Name Client Representative : |  |  |  | Yard invoice currency: | RUB
Project nr.: |  |  |  | EXCHANGE RATE TO CURRENCY
Vessel ID nr - internal: |  |  |  | EUR
SGD
Yard name: |  |  |  | GBP | 0
Yard location: |  |  |  |  | 0
TIMELINES M&R | PLANNED | ACTUAL
Date vessel demobilised:
Start date yard:
Date in dock:
Date out dock:
Finish date yard:
Date vessel mobilised:
Days out of service:
Total Costs Planned Maintenance and Repair
GROUP | TITLE |  |  | BUDGET | COMMITTED | FORECAST | ACTUAL
0 | Crewing and Victuals |  |  | 0 | 0 | 0
1 | Flag state-, class- and management, consumables, transportation |  |  | 0 | 0 | 0 | 0
2 | Ship’s hull,conservation |  |  | 0 | 0 | 0 | 0
3 | Equipment and systems for crew and passengers |  |  | 0 | 0 | 0 | 0
4 | Diesel engines, flexible couplings for DE’s, generators |  |  | 0 | 0 | 0 | 0
5 | Ship propulsion and steering equipment |  |  | 0 | 0 | 0 | 0
6 | Ship specific equipment |  |  | 0 | 0 | 0 | 0
7 | Ship common systems deck department |  |  | 0 | 0 | 0 | 0
8 | Ship common systems engine department |  |  | 0 | 0 | 0 | 0
9 | Alongside repair and dry docking |  |  | 0 | 0 | 0 | 0
10 | Damages |  |  | 0 | 0 | 0 | 0
11 | Modifications |  |  | 0 | 0 | 0 | 0
|  |  | TOTALS | 0 | 0 | 0 | 0
Approved by TSI-P: |  | Date: | Signature: | Approved by CM: |  | Date: | Signature:
Approved by ROM: |  | Date: | Signature: | Approved by RTM: |  | Date: | Signature:
Approved by RMD: |  | Date: | Signature: | Approved by CTO: |  | Date: | Signature:
Approved by BOM: |  | Date: | Signature: | Approved by BOM: |  | Date: | Signature:
Approved by BOM: |  | Date: | Signature:

## Planned M&R Daily Report
FRM-OFF-04-Site Specific Novo-002
| BUDGET CONTROL TOOLS |  |  |  |  | File 04 / Папка 04
Retention 3 Year / Срок
хранения 3 года
Planned M&R Daily Report
0
Name TSI-P : | 0 |  |  | Project Plan Currency: | USD
Name Client Representative : | 0 |  |  | Yard invoice currency: | RUB
Project nr.: | 0 |  |  | EXCHANGE RATE TO CURRENCY
Vessel ID nr - internal: | 0 |  |  | EUR | 0
|  |  |  | SGD | 0
Yard name: | 0 |  |  | GBP | 0
Yard location: | 0 |  |  |  | 0
TIMELINES M&R | PLANNED | ACTUAL
Date vessel demobilised: | 0
Start date yard: | 0
Date in dock: | 0
Date out dock: | 0
Finish date yard: | 0
Date vessel mobilised: | 0
Days out of service: | 0 | 0
Total Costs Planned Maintenance and Repair
GROUP | TITLE |  |  | BUDGET | COMMITTED | FORECAST | ACTUAL
0 | Crewing and Victuals |  |  | 0 | 0 | 0 | 0
1 | Flag state-, class- and management, consumables, transportation |  |  | 0 | 0 | 0 | 0
2 | Ship’s hull,conservation |  |  | 0 | 0 | 0 | 0
3 | Equipment and systems for crew and passengers |  |  | 0 | 0 | 0 | 0
4 | Diesel engines, flexible couplings for DE’s, generators |  |  | 0 | 0 | 0 | 0
5 | Ship propulsion and steering equipment |  |  | 0 | 0 | 0 | 0
6 | Ship specific equipment |  |  | 0 | 0 | 0 | 0
7 | Ship common systems deck department |  |  | 0 | 0 | 0 | 0
8 | Ship common systems engine department |  |  | 0 | 0 | 0 | 0
9 | Alongside repair and dry docking |  |  | 0 | 0 | 0 | 0
10 | Damages |  |  | 0 | 0 | 0 | 0
11 | Modifications |  |  | 0 | 0 | 0 | 0
|  |  | TOTALS | 0 | 0 | 0 | 0
Daily Reporting / Remarks concerning: |  |  |  | Period From: |  | To:

## Group 0
|  |  |  | Main Group 0 | 0
NO. | W.S. | W.V.F. | P.O. | DESCRIPTION | BUDGET | COMMITTED | FORECAST | ACTUAL | REMARKS
0 | Crewing and Victuals
00 |  |  |  | Salaries Permanent Sea staff (at Costs)
|  |  |  | SubTotal | 0 | 0 | 0 | 0
01 |  |  |  | Salaries Sea staff on Consolidated Pay (at Costs)
|  |  |  | SubTotal | 0 | 0 | 0 | 0
02 |  |  |  | Salaries Subcontract Sea staff (at Costs)
|  |  |  | SubTotal | 0 | 0 | 0 | 0
03 |  |  |  | Salaries Day rate Client Contract
|  |  |  | SubTotal | 0 | 0 | 0 | 0
04 |  |  |  | Salaries Lump sum Client Contract
|  |  |  | SubTotal | 0 | 0 | 0 | 0
05 |  |  |  | Disbursement Costs, Crew Medical
|  |  |  | SubTotal | 0 | 0 | 0 | 0
06 |  |  |  | Travel
Tickets on ferry and living in hotel
|  |  |  | SubTotal | 0 | 0 | 0 | 0
07 |  |  |  | Training
|  |  |  | SubTotal | 0 | 0 | 0 | 0
08
|  |  |  | SubTotal | 0 | 0 | 0 | 0
09 |  |  |  | Victuals
|  |  |  | SubTotal | 0 | 0 | 0 | 0
|  |  |  | Total Main Group 0 | 0 | 0 | 0 | 0

## Group 1
|  |  |  | Main Group 1 | 0
NO. | W.S. | W.V.F. | P.O. | DESCRIPTION | BUDGET | COMMITTED | FORECAST | ACTUAL | REMARKS
1 | Flag state-, class- and management, consumables, transportation
10 |  |  |  | Flag state and survey
|  |  |  | SubTotal | 0 | 0 | 0 | 0
11 |  |  |  | Management, inspection, PMS system
|  |  |  | SubTotal | 0 | 0 | 0 | 0
12 |  |  |  | Insurance
|  |  |  | SubTotal | 0 | 0 | 0 | 0
13 |  |  |  | Communication expenses
|  |  |  | SubTotal | 0 | 0 | 0 | 0
14 |  |  |  | Bunkers and lubricating oil
|  |  |  | SubTotal | 0 | 0 | 0 | 0
15 |  |  |  | Engine Stores, including chemicals
|  |  |  | SubTotal | 0 | 0 | 0 | 0
16 |  |  |  | Deck consumables
|  |  |  | SubTotal | 0 | 0 | 0 | 0
17 |  |  |  | Accommodation inventory
|  |  |  | SubTotal | 0 | 0 | 0 | 0
18 |  |  |  | Crew’s working gear, workshop / Store outfit incl. cleaning equipment
|  |  |  | SubTotal | 0 | 0 | 0 | 0
19 |  |  |  | Port expenses, transportation- and logistics expenses
|  |  |  | SubTotal | 0 | 0 | 0 | 0
|  |  |  | Total Main Group 1 | 0 | 0 | 0 | 0

## Group 2
|  |  |  | Main Group 2 | 0
NO. | W.S. | W.V.F. | P.O. | DESCRIPTION | BUDGET | COMMITTED | FORECAST | ACTUAL | REMARKS
2 | Ship’s hull,conservation
20 |  |  |  | Hull structure
Add
|  |  |  | SubTotal | 0 | 0 | 0 | 0
21 |  |  |  | Tanks and void spaces
|  |  |  | SubTotal | 0 | 0 | 0 | 0
22 |  |  |  | Hull outfitting
|  |  |  | SubTotal | 0 | 0 | 0 | 0
23 |  |  |  | Cathodic protection (anodes, impressed current)
|  |  |  | SubTotal | 0 | 0 | 0 | 0
24 |  |  |  | Cathodic protection internal. (anodes, anti-fouling)
|  |  |  | SubTotal | 0 | 0 | 0 | 0
25 |  |  |  | Conservation (paint)
|  |  |  | SubTotal | 0 | 0 | 0 | 0
|  |  |  | Total Main Group 2 | 0 | 0 | 0 | 0

## Group 3
|  |  |  | Main Group 3 | 0
NO. | W.S. | W.V.F. | P.O. | DESCRIPTION | BUDGET | COMMITTED | FORECAST | ACTUAL | REMARKS
3 | Equipment and systems for crew and passengers
30 |  |  |  | Lifesaving, medical equipment, portable fire fighting equipment and personal protection
|  |  |  | SubTotal | 0 | 0 | 0 | 0
31 |  |  |  | Accomodation, insulation, panels, bulkheads, doors, windows, port holes and skylights
|  |  |  | SubTotal | 0 | 0 | 0 | 0
32 |  |  |  | Accomodation, internal deck covering, internal / external ladders, steDAXX, platforms, railings and gangways
|  |  |  | SubTotal | 0 | 0 | 0 | 0
33 |  |  |  | Furniture, inventory, entertainment equipment
|  |  |  | SubTotal | 0 | 0 | 0 | 0
34 |  |  |  | Galley, pantry, laundry equipment, provision plants
|  |  |  | SubTotal | 0 | 0 | 0 | 0
35 |  |  |  | Transport equipment for provisions, stores and engine room equipment
|  |  |  | SubTotal | 0 | 0 | 0 | 0
36 |  |  |  | Accomodation ventilation, air-conditioning, and heating system
|  |  |  | SubTotal | 0 | 0 | 0 | 0
37 |  |  |  | Fresh water (FW) makers
|  |  |  | SubTotal | 0 | 0 | 0 | 0
38 |  |  |  | Hydrophore salt and fresh water systems
|  |  |  | SubTotal | 0 | 0 | 0 | 0
39 |  |  |  | Sewage system
|  |  |  | SubTotal | 0 | 0 | 0 | 0
|  |  |  | Total Main Group 3 | 0 | 0 | 0 | 0

## Group 4
|  |  |  | Main Group 4 | 0
NO. | W.S. | W.V.F. | P.O. | DESCRIPTION | BUDGET | COMMITTED | FORECAST | ACTUAL | REMARKS
4 | Diesel engines, flexible couplings for DE’s, generators
40 |  |  |  | Diesel engine(s) direct for propulsion
|  |  |  | SubTotal | 0 | 0 | 0 | 0
41 |  |  |  | Auxiliary gen.set, diesel engine(s)
|  |  |  | SubTotal | 0 | 0 | 0 | 0
42 |  |  |  | Generator(s) for main electric power production
|  |  |  | SubTotal | 0 | 0 | 0 | 0
43 |  |  |  | Emergency / Harbour gen.set, diesel engine(s)
|  |  |  | SubTotal | 0 | 0 | 0 | 0
44 |  |  |  | Emergency / Harbour gen.set, generator(s)
|  |  |  | SubTotal | 0 | 0 | 0 | 0
45 |  |  |  | Flexible coupling(s), for diesel engine(s), generators and Fi-Fi pumDAXX
|  |  |  | SubTotal | 0 | 0 | 0 | 0
|  |  |  | Total Main Group 4 | 0 | 0 | 0 | 0

## Group 5
|  |  |  | Main Group 5 | 0
NO. | W.S. | W.V.F. | P.O. | DESCRIPTION | BUDGET | COMMITTED | FORECAST | ACTUAL | REMARKS
5 | Ship propulsion and -steering equipment
50 |  |  |  | Electric motor(s) for propulsion
|  |  |  | SubTotal | 0 | 0 | 0 | 0
51 |  |  |  | Flexible coupling(s) for propulsion and drive system
|  |  |  | SubTotal | 0 | 0 | 0 | 0
52 |  |  |  | Fixed pitch propeller(s)
|  |  |  | SubTotal | 0 | 0 | 0 | 0
53 |  |  |  | Controllable pitch propeller(s)
|  |  |  | SubTotal | 0 | 0 | 0 | 0
54 |  |  |  | Rudders) and steering gear
|  |  |  | SubTotal | 0 | 0 | 0 | 0
55 |  |  |  | Propulsion thruster(s)
|  |  |  | SubTotal | 0 | 0 | 0 | 0
56 |  |  |  | Waterjet(s)
|  |  |  | SubTotal | 0 | 0 | 0 | 0
57 |  |  |  | Bow thruster(s)
|  |  |  | SubTotal | 0 | 0 | 0 | 0
58 |  |  |  | Stern thruster(s)
|  |  |  | SubTotal | 0 | 0 | 0 | 0
59 |  |  |  | Stabilizer system, bubble plant (manoeuvring in ice)
|  |  |  | SubTotal | 0 | 0 | 0 | 0
|  |  |  | Total Main Group 5 | 0 | 0 | 0 | 0

## Group 6
|  |  |  | Main Group 6 | 0
NO. | W.S. | W.V.F. | P.O. | DESCRIPTION | BUDGET | COMMITTED | FORECAST | ACTUAL | REMARKS
6 | Ship specific equipment
60 |  |  |  | Towing- and anchor handling equipment
|  |  |  | SubTotal | 0 | 0 | 0 | 0
61 |  |  |  | Deck Crane(s)
|  |  |  | SubTotal | 0 | 0 | 0 | 0
62 |  |  |  | System(s) for liquid cargo
|  |  |  | SubTotal | 0 | 0 | 0 | 0
63 |  |  |  | Saturation diving equipment
|  |  |  | SubTotal | 0 | 0 | 0 | 0
64 |  |  |  | Air diving equipment
|  |  |  | SubTotal | 0 | 0 | 0 | 0
65 |  |  |  | ROV equipment
|  |  |  | SubTotal | 0 | 0 | 0 | 0
66 |  |  |  | Other ship specific equipment
|  |  |  | SubTotal | 0 | 0 | 0 | 0
|  |  |  | Total Main Group 6 | 0 | 0 | 0 | 0

## Group 7
|  |  |  | Main Group 7 | 0
NO. | W.S. | W.V.F. | P.O. | DESCRIPTION | BUDGET | COMMITTED | FORECAST | ACTUAL | REMARKS
7 | Ship common systems deck department
70 |  |  |  | Navigation equipment
|  |  |  | SubTotal | 0 | 0 | 0 | 0
71 |  |  |  | Communication equipment
|  |  |  | SubTotal | 0 | 0 | 0 | 0
72 |  |  |  | Dynamic positioning (DP) equipment
|  |  |  | SubTotal | 0 | 0 | 0 | 0
73 |  |  |  | Closed circuit TV systems
|  |  |  | SubTotal | 0 | 0 | 0 | 0
74 |  |  |  | Anchor- and mooring equipment
|  |  |  | SubTotal | 0 | 0 | 0 | 0
75 |  |  |  | Fire- and life boat alarm, firefighting- and wash down systems
|  |  |  | SubTotal | 0 | 0 | 0 | 0
76 |  |  |  | Bilge- and Ballast systems, scupper pipes outside
|  |  |  | SubTotal | 0 | 0 | 0 | 0
77 |  |  |  | Aeration- and sounding systems from tanks to deck
|  |  |  | SubTotal | 0 | 0 | 0 | 0
|  |  |  | Total Main Group 7 | 0 | 0 | 0 | 0

## Group 8
|  |  |  | Main Group 8 | 0
NO. | W.S. | W.V.F. | P.O. | DESCRIPTION | BUDGET | COMMITTED | FORECAST | ACTUAL | REMARKS
8 | Ship common systems engine department
80 |  |  |  | Fuel systems
81
82
|  |  |  | SubTotal | 0 | 0 | 0 | 0
83 |  |  |  | Compressed air systems
84
|  |  |  | SubTotal | 0 | 0 | 0 | 0
85 |  |  |  | Other ship common systems
|  |  |  | SubTotal | 0 | 0 | 0 | 0
86 |  |  |  | Electric power distribution system, incl. cable installations
|  |  |  | SubTotal | 0 | 0 | 0 | 0
87 |  |  |  | Lighting systems, incl. emergency lighting
|  |  |  | SubTotal | 0 | 0 | 0 | 0
88 |  |  |  | Remote control systems for propulsion- and maneuvering equipment
|  |  |  | SubTotal | 0 | 0 | 0 | 0
89 |  |  |  | Alarm- and monitoring and automation systems for machinery
|  |  |  | SubTotal | 0 | 0 | 0 | 0
|  |  |  | Total Main Group 8 | 0 | 0 | 0 | 0

## Group 9
|  |  |  | Main Group 9 | 0
NO. | W.S. | W.V.F. | P.O. | DESCRIPTION | BUDGET | COMMITTED | FORECAST | ACTUAL | REMARKS
9 | Alongside repair and dry docking
90
91
92
|  |  |  | SubTotal | 0 | 0 | 0 | 0
93 |  |  |  | Temporary covering and gear
|  |  |  | SubTotal | 0 | 0 | 0 | 0
94 |  |  |  | Testing during / after docking
|  |  |  | SubTotal | 0 | 0 | 0 | 0
95 |  |  |  | Delivery trip and trials
|  |  |  | SubTotal | 0 | 0 | 0 | 0
|  |  |  | Total Main Group 9 | 0 | 0 | 0 | 0

## Group 10 Damages
|  |  |  | Group 10 Damages | 0
NO. | W.S. | W.V.F. | P.O. | DESCRIPTION | BUDGET | COMMITTED | FORECAST | ACTUAL | REMARKS
10 | Damages
100 |  |  |  | Damages
|  |  |  | SubTotal | 0 | 0 | 0 | 0
|  |  |  | Total Group 10 Damages | 0 | 0 | 0 | 0

## Group 11 Modifications
|  |  |  | Group 11 Modifications | 0
NO. | W.S. | W.V.F. | P.O. | DESCRIPTION | BUDGET | COMMITTED | FORECAST | ACTUAL | REMARKS
11 | Modifications
110 |  |  |  | Modifications
|  |  |  | SubTotal | 0 | 0 | 0 | 0
|  |  |  | Total Group 11 Modifications | 0 | 0 | 0 | 0

## W.S. Overview
Overview work specifications and prices
0
Planned M&R execution date:
Name Yard: |  |  |  |  | 0
Estimated continuous running days:
NO. | W.S. | Y | S | Brief description of the work |  | Estimated price | Quoted price | Related requisition | Related P.O. | Executed by | Remarks
1
2
2
3
3
4
4
5
5
6
6
7
7
8
8
9
9
10
10
11
11
12
12
13
13
14
14
15
15
16
16
17
17
18
18
19
19
20
20
21
21
22
22
23
23
24
24
25
25
26
26
27
27
28
28
29
29
30
30
31
31
32
32
33
33
34
34
35
35
36
36
37
37
38
38
39
39
40
40
41
41
42
42
43
43
44
44
45
45
46
46
47
47
48
48
49
49
50
50
51
51
52
52
53
53
54
54
55
55
56

## Req._P.O. Overview
Spares Requirements for Dry Docking
0
Planned M&R execution date:
Req No | Related W.S. No | Parts Description | P.O. | Estimated amount | Fixed amount | Remarks from purchasing
0