## Planning (2)
|  | PLANNING DD FORM /ПЛАНИРОВАНИЕ РАБОТ В ДОКЕ | [22 empty] | FRM-OFF-04-Site Specific Novo-003
File 04 / Папка 04
Retention 3 Year / Срок
хранения 3 года
[6 empty] | Date | 2017-11-08
Today
Phase | Description | Priority | sequence | People Required | Duration | Starting | Ending | Status | Days Remai ning | time axis 2017-03-30 to 2018-10-08
0 | Print area start date |  |  |  | -42823 | 2017-03-30
1 | AX Project No Created, TSI(P) Allocated |  |  |  | 1 | 2016-06-01 | 2016-06-01 | Actual | -525
2 | Initial scope & Budget defined |  |  |  | 122 | 2016-06-01 | 2016-09-30 | Actual | -404
3 | Operations Alignment completed |  |  |  | 1 | 2016-12-02 | 2016-12-02 | Actual | -341
4 | Long lead spare parts PO's placed |  |  |  | 181 | 2016-10-01 | 2017-03-30 | Potential | -223 | bar: 2017-03-30
5 | Final work spec defined |  |  |  | 31 | 2016-09-30 | 2016-10-30 | Actual | -374
6 | Yard Tender issued |  |  |  | 30 | 2016-11-01 | 2016-11-30 | Actual | -343
7 | Project Plan Approved |  |  |  | 29 | 2017-01-02 | 2017-01-30 |  | -282
8 | Yard contract awarded |  |  |  | 28 | 2017-02-01 | 2017-02-28 |  | -253
9 | Start Yard Period |  |  |  | 59 | 2017-04-03 | 2017-05-31 |  | -161 | bar: 2017-04-03 to 2017-05-31
| Arrival in yard. Mooring alongside.Прибытие в завод. Швартовка у причала. |  | F | C | 1 | 2017-04-03 | 2017-04-03 |  | -219 | bar: 2017-04-03
| DD intake. Постановка в док. |  | D | O | 1 | 2017-04-04 | 2017-04-04 |  | -218 | bar: 2017-04-04
| Docking period Доковый период |  | D |  | 21 | 2017-04-04 | 2017-04-24 |  | -198 | bar: 2017-04-04 to 2017-04-24
| Shore power / fire water / sewage, connect / disconnect |  | D | O | 21 | 2017-04-04 | 2017-04-24 |  | -198 | bar: 2017-04-04 to 2017-04-24
| Hull washing / scraping |  | D | O | 2 | 2017-04-04 | 2017-04-05 |  | -217 | bar: 2017-04-04 to 2017-04-05
| Dismantle all fenders |  | D | S | 2 | 2017-04-05 | 2017-04-06 |  | -216 | bar: 2017-04-05 to 2017-04-06
| Thickness measurements Замеры остаточных толщин |  | D | O | 3 | 2017-04-05 | 2017-04-07 |  | -215 | bar: 2017-04-05 to 2017-04-07
| Hull sand blasting/ |  | D | O | 4 | 2017-04-06 | 2017-04-09 |  | -213 | bar: 2017-04-06 to 2017-04-09
| Hull anticorrosion paint first apply |  | D | O | 5 | 2017-04-06 | 2017-04-10 |  | -212 | bar: 2017-04-06 to 2017-04-10
| Bottom anticorrosion paint second apply |  | D | O | 2 | 2017-04-10 | 2017-04-11 |  | -211 | bar: 2017-04-10 to 2017-04-11
| Hull/exept bottom/ paint second apply |  | D | O | 3 | 2017-04-11 | 2017-04-13 |  | -209 | bar: 2017-04-11 to 2017-04-13
| Bottom antifouling paint apply |  | D | O | 2 | 2017-04-22 | 2017-04-23 |  | -199 | bar: 2017-04-22 to 2017-04-23
| All marks apply |  | D | O | 1 | 2017-04-23 | 2017-04-23 |  | -199 | bar: 2017-04-23
| Inspection/Replacement zinc protectors |  | D | O | 3 | 2017-04-11 | 2017-04-13 |  | -209 | bar: 2017-04-11 to 2017-04-13
| Sea chests hydraulic test |  | D | O | 4 | 2017-04-13 | 2017-04-16 |  | -206 | bar: 2017-04-13 to 2017-04-16
| Replacement oil seals and liner of Std Thruster |  | D | Ss | 6 | 2017-04-11 | 2017-04-16 |  | -206 | bar: 2017-04-11 to 2017-04-16
| Replacement oil seals of Port Trust |  | D | Ss | 7 | 2017-04-16 | 2017-04-22 |  | -200 | bar: 2017-04-16 to 2017-04-22
| Outboard valves overhauling Разборка, дефектовка, тест, сборка ДЗА |  | D | M | 15 | 2017-04-07 | 2017-04-21 |  | -201 | bar: 2017-04-07 to 2017-04-21
| Outboard SW valves and scuppers overhauling/Ремонт отливных клапанов и шпигатов |  | D | M | 12 | 2017-04-09 | 2017-04-20 |  | -202 | bar: 2017-04-09 to 2017-04-20
| Fenders renewal and repairing Замена и ремонт кранцевой защиты |  | D | S | 11 | 2017-04-09 | 2017-04-19 |  | -203 | bar: 2017-04-09 to 2017-04-19
| Steel repairs FWD fenders and railing |  | D | S | 6 | 2017-04-09 | 2017-04-14 |  | -208 | bar: 2017-04-09 to 2017-04-14
| Anchors and anchor chaqin layout, cleaning, checking, painting, marking. Работы с якорями и якорными цепями |  | D | M | 8 | 2017-04-09 | 2017-04-16 |  | -206 | bar: 2017-04-09 to 2017-04-16
| Renovation of anchor hawse pipe |  | D | S | 5 | 2017-04-10 | 2017-04-14 |  | -208 | bar: 2017-04-10 to 2017-04-14
| Cleaning and painting of water tanks |  | D | P | 5 | 2017-04-05 | 2017-04-09 |  | -213 | bar: 2017-04-05 to 2017-04-09
| Cleaning and painting of sewage tank |  | D | P | 3 | 2017-04-07 | 2017-04-09 |  | -213 | bar: 2017-04-07 to 2017-04-09
| Cleaning and painting of ballast tank |  | D | P | 5 | 2017-04-09 | 2017-04-13 |  | -209 | bar: 2017-04-09 to 2017-04-13
| Cleaning and painting of bilge tank |  | D | P | 4 | 2017-04-11 | 2017-04-14 |  | -208 | bar: 2017-04-11 to 2017-04-14
| Repair of vent pipes with heads |  | D | M | 6 | 2017-04-09 | 2017-04-14 |  | -208 | bar: 2017-04-09 to 2017-04-14
| Repair of drain pipe and scuppers |  | F | M | 15 | 2017-04-09 | 2017-04-23 |  | -199 | bar: 2017-04-09 to 2017-04-23
| RMRS survey before undocking |  | D | O | 1 | 2017-04-24 | 2017-04-24 |  | -198 | bar: 2017-04-24
| Repair of FWD winches |  | D/F | Ss | 21 | 2017-04-10 | 2017-04-30 |  | -192 | bar: 2017-04-10 to 2017-04-30
| Repair of system hydraulic |  | D/F | Ss | 21 | 2017-04-10 | 2017-04-30 |  | -192 | bar: 2017-04-10 to 2017-04-30
| Repair of hydro motors |  | D/F | Ss | 13 | 2017-04-16 | 2017-04-28 |  | -194 | bar: 2017-04-16 to 2017-04-28
| Replacement of flexible hoses |  | F | Ss | 2 | 2017-04-28 | 2017-04-29 |  | -193 | bar: 2017-04-28 to 2017-04-29
| Maintenance of AFT winch |  | F | Ss | 11 | 2017-04-29 | 2017-05-09 |  | -183 | bar: 2017-04-29 to 2017-05-09
| Safe guard for FWD & AFT winches hydraulic pipes to be fabricated |  | F | M | 7 | 2017-05-09 | 2017-05-15 |  | -177 | bar: 2017-05-09 to 2017-05-15
| Check and adjustment of winches |  | F | M | 3 | 2017-05-15 | 2017-05-17 |  | -175 | bar: 2017-05-15 to 2017-05-17
| Repair of towing hook |  | F | E | 6 | 2017-04-26 | 2017-05-01 |  | -191 | bar: 2017-04-26 to 2017-05-01
| Replacement of flexible hoses crane |  | F | M | 2 | 2017-05-02 | 2017-05-03 |  | -189 | bar: 2017-05-02 to 2017-05-03
| Repair of pipe crane |  | F | M | 6 | 2017-05-03 | 2017-05-08 |  | -184 | bar: 2017-05-03 to 2017-05-08
| Repair of el.motor crane |  | F | E | 10 | 2017-05-03 | 2017-05-12 |  | -180 | bar: 2017-05-03 to 2017-05-12
| Repair of FI-FI monitor |  | F | M | 7 | 2017-05-12 | 2017-05-18 |  | -174 | bar: 2017-05-12 to 2017-05-18
| ME's overhaul |  | D/F | Ms | 31 | 2017-04-10 | 2017-05-10 |  | -182 | bar: 2017-04-10 to 2017-05-10
| LO coolers chemical cleaning |  | F | M | 11 | 2017-04-30 | 2017-05-10 |  | -182 | bar: 2017-04-30 to 2017-05-10
| SW coolers chemical cleaning |  | F | M | 11 | 2017-04-30 | 2017-05-10 |  | -182 | bar: 2017-04-30 to 2017-05-10
| Overhaul clutch |  | F | Ms | 11 | 2017-05-10 | 2017-05-20 |  | -172 | bar: 2017-05-10 to 2017-05-20
| Inspection and adjustment control and alarm systems of the ZP-31 |  | F | E | 7 | 2017-05-20 | 2017-05-26 |  | -166 | bar: 2017-05-20 to 2017-05-26
| Main clutch control and alarm systems maintenance inspection |  | F | E | 7 | 2017-05-20 | 2017-05-26 |  | -166 | bar: 2017-05-20 to 2017-05-26
| AUX engines overhaul |  | D/F | Ms | 22 | 2017-04-11 | 2017-05-02 |  | -190 | bar: 2017-04-11 to 2017-05-02
| Generators Overhaul |  | D/F | E | 22 | 2017-04-11 | 2017-05-02 |  | -190 | bar: 2017-04-11 to 2017-05-02
| Repair of bilge pumps with el.motor |  | F | ME | 4 | 2017-04-25 | 2017-04-28 |  | -194 | bar: 2017-04-25 to 2017-04-28
| Replacement of bilge pump |  | F | M | 4 | 2017-04-25 | 2017-04-28 |  | -194 | bar: 2017-04-25 to 2017-04-28
| Repair of fuel oil transfer pump with drive motor |  | F | M | 5 | 2017-04-27 | 2017-05-01 |  | -191 | bar: 2017-04-27 to 2017-05-01
| Repair of Pre-lub pumps with el motors |  | F | ME | 5 | 2017-05-01 | 2017-05-05 |  | -187 | bar: 2017-05-01 to 2017-05-05
| Repair of FW emergency cooling pump with el motor |  | F | ME | 4 | 2017-05-05 | 2017-05-08 |  | -184 | bar: 2017-05-05 to 2017-05-08
| Repair of fire pumps with el. Motor |  | F | ME | 5 | 2017-05-08 | 2017-05-12 |  | -180 | bar: 2017-05-08 to 2017-05-12
| Repair of main service pump with el.motor |  | F | ME | 4 | 2017-05-12 | 2017-05-15 |  | -177 | bar: 2017-05-12 to 2017-05-15
| Repair of air compressor with el motor |  | F | ME | 4 | 2017-05-16 | 2017-05-19 |  | -173 | bar: 2017-05-16 to 2017-05-19
| Repair of el.motors for ventilation |  | F | ME | 4 | 2017-05-19 | 2017-05-22 |  | -170 | bar: 2017-05-19 to 2017-05-22
| Repair of el. Motor ventilation from the galley |  | F | E | 3 | 2017-05-17 | 2017-05-19 |  | -173 | bar: 2017-05-17 to 2017-05-19
| Machinery and Electric jobs Работы по дефектовке насосов |  | F | E | 28 | 2017-04-25 | 2017-05-22 |  | -170 | bar: 2017-04-25 to 2017-05-22
| Check and repair of alarm system |  | F | E | 7 | 2017-05-20 | 2017-05-26 |  | -166 | bar: 2017-05-20 to 2017-05-26
| Maintenance and hydraulic test of CO2 system |  | F | Ss | 31 | 2017-04-26 | 2017-05-26 |  | -166 | bar: 2017-04-26 to 2017-05-26
| Hydraulic test of fire system |  | F | M | 5 | 2017-05-15 | 2017-05-19 |  | -173 | bar: 2017-05-15 to 2017-05-19
| Repair and hydraulic test main air bottles |  | F | M | 8 | 2017-05-19 | 2017-05-26 |  | -166 | bar: 2017-05-19 to 2017-05-26
| Air system inspection maintenance |  | F | M | 3 | 2017-05-26 | 2017-05-28 |  | -164 | bar: 2017-05-26 to 2017-05-28
| Replacement of accumulator batteries |  | F | C | 2 | 2017-04-24 | 2017-04-25 |  | -197 | bar: 2017-04-24 to 2017-04-25
| Check of main circuit breakers |  | F | E | 15 | 2017-04-27 | 2017-05-11 |  | -181 | bar: 2017-04-27 to 2017-05-11
| Check of insulation resistance |  | F | E | 15 | 2017-04-27 | 2017-05-11 |  | -181 | bar: 2017-04-27 to 2017-05-11
| Replacement of internal door |  | F | M | 7 | 2017-04-27 | 2017-05-03 |  | -189 | bar: 2017-04-27 to 2017-05-03
| Replacement of doors and port holes rubber seals |  | F | M | 8 | 2017-05-03 | 2017-05-10 |  | -182 | bar: 2017-05-03 to 2017-05-10
| Replacement of linoleum |  | F | M | 8 | 2017-05-03 | 2017-05-10 |  | -182 | bar: 2017-05-03 to 2017-05-10
| Repair of window wiper systems |  | F | M | 3 | 2017-05-10 | 2017-05-12 |  | -180 | bar: 2017-05-10 to 2017-05-12
| Repair of shower room |  | F | M | 15 | 2017-05-10 | 2017-05-24 |  | -168 | bar: 2017-05-10 to 2017-05-24
| Replacement tile in galley |  | F | M | 15 | 2017-05-10 | 2017-05-24 |  | -168 | bar: 2017-05-10 to 2017-05-24
| Vessel cleaning and sea trial Замывка судна/ходовые испытания |  | F | MC | 2 | 2017-05-28 | 2017-05-29 |  | -163 | bar: 2017-05-28 to 2017-05-29
| Magnetic compass adjustment |  | F | Ss | 1 | 2017-05-29 | 2017-05-29 |  | -163 | bar: 2017-05-29
| RMRS special survey completion Завершение освидетельствования РМРС |  | F | Ss | 1 | 2017-05-30 | 2017-05-30 |  | -162 | bar: 2017-05-30
| Bunkering and departure Бункеровка/отход судна в рейс |  | F | C | 2 | 2017-05-30 | 2017-05-31 |  | -161 | bar: 2017-05-30 to 2017-05-31
10 | Project Closing |  |  |  | 31 | 2017-05-30 | 2017-06-29 |  | -132 | bar: 2017-05-30 to 2017-06-29
| Paint |  |  | P
| Steel |  |  | S
| Mechanical yard |  |  | M
| Mechanical subcontractor |  |  | Ms
| Electric |  |  | E
| Crew |  |  | C
| Other |  |  | O
| Specialized subcontractor |  |  | Ss
| Dock job |  | D
| Floating job |  | F
Head of technical department 07.11.2017

## Sheet3
Phase # | Phase Name
1 | AX Project No Created, TSI(P) Allocated
2 | Initial scope & Budget defined
3 | Operations Alignment completed
4 | Long lead spare parts PO's placed
5 | Final work spec defined
6 | Yard Tender issued
7 | Project Plan Approved
8 | Yard contract awarded
9 | Start Yard Period
10 | Project Closing
Corridors, stairs, mess rooms, accommodation protection by plastic paper Изоляция палуб, иллюминаторов, механизвмов полиэтиленовой пленкой.(ЭКИПАЖ)
FO Tanks cleaning Зачистка топливных танков
Docking period Доковый период
Shore power / fire water / sewage, connect / disconnect
Hull washing / scraping
Thickness measurements Замеры остаточных толщин
Removal propellers
Replacement oil seals and liner of Std Truster
Replacement oil seals of Port Trust
Inspection and adjustment control and alarm systems of the ZP-31
Overhall clutch
Main clutch control and alarm systems maintenance inspection
Dismantle all fenders
Steel repairs FWD fenders and railing
Cleaning and painting of water tanks
Cleaning and painting of seawage tank
Cleaning and painting of ballast tank
Cleaning and painting of bildge tank
Repair of vent pipes with heads
Repair of drane pipe and scuppers
Anchors layout, cleaning, checking, painting, marking Работы с якорями и якорными цепями
Renovation of anchor hawse pipe
Hull blasting, painting Замывка корпуса, пескоструйная зачистка, покраска
Outboard valves overhauling Разборка, дефектовка, тест, сборка ДЗА
Repair of FWD winches
Replacement of flexible hoses
Repair of system hydraulic
Maintenance of AFT winch
Check and adjustment of winches
Repair of hydromotors
Repair of towing hook
Safe guard for FWD & AFT winches hydraulic pipes to be fabricated
Replacement of flexible hoses crane
Repair of pipe crane
Repair of el.motor crane
Repair of FI-FI monitor
Maintenance and hydraulic test of CO2 system
Repair of fire pumps with el. Motor
Hydraulic test of fire system
ME's overhaul
AUX engines overhaul
Generators Overhaul
Machinery and Electric jobs Работы по дефектовке насосов
Repair of bildge pumps with el.motor
Repalcement of bildge pump
Repair of fuel oil transfer pump with drive motor
LO coolers chemical cleaning
Repair of Pre-lub pumps with el motors
SW coolers chemical cleaning
Repair of FW emergency cooling pump with el motor
Repair of SW valves, pipes.
Repair of main service pump with el.motor
Repair of air compressor with el motor
Repair and hydraulic test main air bottles
Air system inspection maintenance
Replacement of accumulator batteries
Check of main circuit breakers
Check of insulation resistance
Chek and repair of alarm system
Repair of el.motors for ventilation
Replacement of internal door
Replacement of doors and port holes rubber seals
Peplacement of linoleum
Rapair of window wiper systems
Repair of shower room
Replacement tile in galley
Repair of el. Motor ventilation from the galley
Inspect/renew anodes Замена цинковых протекторов
Fenders renewal and repairing Замена и ремонт кранцевой защиты
Install propellors
Shafts alignment checking Проверка центровки валовой линии
Vessel cleaning and sea trial Замывка судна/ходовые испытания
Magnetic compass adjustment
RMRS special survey completion Завершение освидетельствования РМРС
Bunkering and departure Бункеровка/отход судна в рейс

## Planning
Soll Taman
Rev 01 17-01-2017
Date | 2017-11-08
Item | Description | Priority | sequence | People Required | Duration | Starting | Ending | Status | Days Remaining | time axis 2017-04-01 to 2017-07-06
| Yard period |  |  |  | 49 | 2017-04-01 | 2017-05-20 |  | -172 | bar: 2017-04-01 to 2017-05-20
[25 empty] | Actual | DRE
[25 empty] | Potential | S/R
[25 empty] | Cancelled | SHE
CONV
CHPP
ELE
S/L
Other